## Sheet1
940 - PRODUCT BACKLOG
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13
Identifier | Description (Customize based on your needs) | Initial Est | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22
This could include date requested, requester, subsystem...
UC1 | Use Case 1 - Do something important |  | 2019-05-20: 5; 2019-05-27: 0
UC2 | Use Case 2 - Do something else important |  | 2019-05-20: 6; 2019-05-27: 7; 2019-06-03: 4
TD1 | A technical debt that needs addressing |  | 2019-05-20: 7; 2019-05-27: 7; 2019-06-03: 4
Bug1 | Some important bug |  | 2019-05-20: 3; 2019-05-27: 3; 2019-06-03: 1
Feat1 | New feature |  | 2019-05-20: 4; 2019-05-27: 4; 2019-06-03: 4
WI1 | A wish item |  | 2019-05-20: 2; 2019-05-27: 4; 2019-06-03: 4
|  |  | 27 | 25 | 17
Out of Money / Time / Interest ...
UC3 | Bla Bla Bla |  | 2019-05-20: 2; 2019-05-27: 2; 2019-06-03: 2
UC4 | Bla Bla Bla |  | 2019-05-20: 3; 2019-05-27: 3; 2019-06-03: 3
Bug2 | Bla Bla Bla |  | 2019-05-20: 4; 2019-05-27: 4; 2019-06-03: 4
Bug3 | Bla Bla Bla |  | 2019-05-20: 5; 2019-05-27: 5; 2019-06-03: 5
Bug4 | Bla Bla Bla |  | 2019-05-27: 5; 2019-06-03: 5
Bug5 | Bla Bla Bla |  | 2019-06-03: 5
| Total Remaining Stones |  | 2019-05-20: 68; 2019-05-27: 69; 2019-06-03: 58
| Est Stones Per Sprint |  | 2019-05-20: 3; 2019-05-27: 3; 2019-06-03: 3
| Remaining Sprints |  | 2019-05-20: 22.6667; 2019-05-27: 23; 2019-06-03: 19.3333